## Awais Shokat
QA Testing Activity Sheet
Prepared by = Muhammad Awais Shokat | [11 empty] | Bug Severity
SR# | Project | Platform | Plan | Ver | Developer Name | QA Name | Task | Task Title | Start date | Task Status | Test Cases | Blocker | Major | Med | Defects Count | Reopen/Fixes Count | Build Status
1 | PMS (KPI'S) | Web |  | 3.6 | Muhammad Arsalan | Muhmmad Awais | 112986 | Update Print Button Text | 2025-06-05 | QA Verified | 1 |  |  |  |  | 0 | Stage
2 | PMS (KPI'S) | Web |  | 3.6 | Muhammad Arsalan, Yasir Lashari | Muhmmad Awais | 112987 | Reverse Formula in Comparison Reports | 2025-06-25 | QA Unverified | 6 |  | 1 |  | 1 | 1 | Stage
3 | PMS (KPI'S) | Web |  | 3.6 | Muhammad Arsalan, Yasir Lashari | Muhmmad Awais | 112988 | Sorting Order in Report Builder | 2025-06-05 | QA Verified | 2 |  |  |  |  | 0 | Stage
4 | PMS (KPI'S) | Web |  | 3.6 | Muhammad Arsalan, Yasir Lashari | Muhmmad Awais | 112989 | Updation in Comparison Regular Report | 2025-06-25 | QA Unverified | 5 | 1 | 1 | 1 | 3 | 2 | Stage
5 | PMS (KPI'S) | Web |  | 3.6 | Muhammad Arsalan, Yasir Lashari | Muhmmad Awais | 112990 | Display Hierarchy in Maktoob Report | 2025-06-05 | QA Verified | 1 |  |  |  |  | 0 | Stage
6 | PMS (KPI'S) | Web |  | 3.6 | Muhammad Arsalan | Muhmmad Awais | 112992 | Update Skype text with Teams | 2025-06-05 | QA Verified | 1 |  |  |  |  | 0 | Stage
1 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 111471 | Header Section (User Side) | 2025-06-30 | Under Q/A
2 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 111473 | Menu / Navbar / Pages | 2025-06-30 | Under Q/A
3 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 111474 | Home Page | 2025-06-30 | Under Q/A
4 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 111475 | Courses | 2025-06-30 | Under Q/A
5 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 111476 | About US | 2025-06-30 | Under Q/A
6 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 111477 | Contact US | 2025-06-30 | Under Q/A
7 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 111478 | Events | 2025-06-30 | Under Q/A
8 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 111479 | Language | N/A | Under Development
9 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 111480 | Register / Sign in | N/A | Under Development
10 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 111481 | Slider | 2025-06-30 | Under Q/A
11 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 111482 | Introduction | 2025-06-30 | Under Q/A
12 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 111483 | Quantitative Course Overview | N/A | Under Development
13 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 111485 | Courses List | 2025-06-30 | Under Q/A
14 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 111486 | Upcoming Courses | 2025-06-30 | Under Q/A
15 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 111487 | Footer | 2025-06-30 | Under Q/A
16 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 113377 | Header Section (Admin Side) | N/A | Under Development
17 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 113378 | Dashboard | N/A | Under Development
18 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 113379 | Side Bar | N/A | Under Development
19 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 113382 | User's | N/A | Under Development
20 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 113383 | Role & Role Permission | N/A | Under Development
21 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 113384 | Categories | N/A | Under Development
22 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 113385 | Courses | N/A | Under Development
23 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 113386 | Questions | N/A | Under Development
24 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 113387 | Batches | N/A | Under Development
25 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 113388 | Events | N/A | Under Development
26 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 113389 | Attendance | N/A | Under Development
27 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 113390 | Niyyat Form | N/A | Under Development
28 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 113391 | Certificate | N/A | Under Development
29 | Madani Courses | Web | 1 | 1 | Muhammad Azeem | Muhmmad Awais | 113392 | Contact Us | N/A | Under Development